## optimised team maker
Optimised Team Maker
Manage timelines and keep track of where your project stands.
This month
Name | Subitems | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Last Updated | Dependency
Software installation |  |  | 2023-09-13 | Done | High | 2023-09-14 | 2023-09-16 | Avinash Ponnada Oct 16, 2023 05:05 PM
Software Requirements for the Project |  | Avinash Ponnada | 2023-09-22 | Done | Medium | 2023-09-23 | 2023-09-25 | Avinash Ponnada Oct 16, 2023 05:08 PM
Front-end Development |  |  | 2023-10-14 | Done | High | 2023-09-29 | 2023-10-14 | Avinash Ponnada Oct 16, 2023 05:09 PM
Algorithm for Fetching aptimised Team |  |  | 2023-10-20 | Done | High | 2023-10-05 | 2023-10-05 | Avinash Ponnada Oct 16, 2023 05:04 PM
Capture the list of Team's in file and send to the respective members |  |  | 2023-10-31 | Not Started |  | 2023-11-01 | 2023-11-07 | Avinash Ponnada Oct 16, 2023 05:10 PM
|  |  | 2023-09-13 to 2023-10-31 |  |  | 2023-09-14 | 2023-11-07