## optimised team maker
Optimised Team Maker
Manage timelines and keep track of where your project stands.
This month
Name | Subitems | Owner | Due Date | Status | Priority | Notes | Timeline - Start | Timeline - End | Last Updated | Dependency
Software Requirements for the Project |  | Bharath | 2023-09-13 | Done | High | Software requirements define what the system must do (functional) and its qualities (non-functional). Crucial for development, they guide design, implementation, and testing, ensuring the system aligns with stakeholders' needs. | 2023-09-14 | 2023-09-16 | Avinash Ponnada Oct 16, 2023 05:05 PM
Software Installation |  | Avinash | 2023-09-22 | Done | Medium | Software installation is the process of loading a program onto a computer. It typically involves running an installer that copies program files, configures settings, and creates shortcuts for easy access. | 2023-09-23 | 2023-09-25 | Avinash Ponnada Oct 16, 2023 05:08 PM
Front-end Development |  | Hari Krishna | 2023-10-14 | Done | High | Front-end development involves creating and implementing the user interface of a website or application. It focuses on the design, layout, and interaction elements that users directly engage with. | 2023-09-29 | 2023-10-14 | Avinash Ponnada Oct 16, 2023 05:09 PM
Algorithm for Fetching optimised Team |  | Avinash | 2023-10-20 | Done | High | The algorithm for fetching an optimized team involves analyzing individual skills, experiences, and performance, utilizing this data to suggest ideal team compositions, and allowing manual adjustments for personalized considerations. | 2023-10-05 | 2023-10-05 | Avinash Ponnada Oct 16, 2023 05:04 PM
Capture the list of Team's in file and send to the respective members |  | Venkatesh | 2023-10-31 | Not Started | High |  | 2023-11-01 | 2023-11-07 | Avinash Ponnada Oct 16, 2023 05:10 PM
|  |  | 2023-09-13 to 2023-10-31 |  |  |  | 2023-09-14 | 2023-11-07